# ENSF - 400 : Assignment 3

# ENSF - 400 : Assignment 3

Winter 2026

Department of Electrical and Software Engineering Schulich School of Engineering

Due: March 9, 2026 at 11:59 PM

# Purpose:

In real IT projects, delivering on time is just as important as delivering correct functionality. Even well - designed systems can fail if schedules are unrealistic or poorly planned. This assignment focuses on transforming your project plan into a realistic timeline. Building on your previously developed SRS and WBS, you will create a project schedule that shows how the work will be organized over time.

# Administrative Details:

- Work within your existing course project group to complete this assignment.

- The submission should be a single PDF file.

- Name the submitted file as Assignment 3 _ENSF 400 _Section#_Group#. For example: Assignment 3 _ENSF 400 _L01_Group01.

- Include the group members' names and UCIDs at the top of the file.

# Part 1: Activity Definition and Sequencing

Using your work Breakdown Structure (WBS) from Assignment 2:

- Break each work package into specific scheduled activities.

- Activities must be action-oriented and verb-based.

Example:

| Work Package | Activities |
| --- | --- |
| User Authentication Module | Design login UI, Implement backend API, Unit testing |

Then create an activity list table that includes:

- Activity ID: a unique identifier for each activity.

- Activity Name: descriptive and verb-oriented.

- Related WBS ID: reference the corresponding WBS element.

- Description: brief explanation of the activity.

- Estimated Duration:provide a time estimate for each activity using a consistent unit (hours, days, or weeks). All activities must use the same unit.

Tip: Be precise and realistic with durations; avoid vague estimates like “short” or “long.”

# Part 2: Network Diagram and Critical Path

- Using your activity list table, create a Network Diagram that clearly shows:

- Dependencies between activities

- Duration of each activity.

- Identify the Critical Path, which is the sequence of activities that determines the shortest project duration.

- Calculate the Total Project Duration based on the critical path.

Ensure your network diagram is neat and readable.

# Submission Guidelines

Submit one PDF document to D2L that includes:

- Activity list table.

- Network diagram and critical path analysis.

- Identified critical path and total project duration.

# Part 1: Activity Definition and Sequencing

# Part 1: Activity Definition and Sequencing

Using your Work Breakdown Structure (WBS) from Assignment 2:

- Break each work package into specific scheduled activities.

- Activities must be action-oriented and verb-based.

Example:

| Work Package | Activities |
| --- | --- |
| User Authentication Module | Design login UI, Implement backend API, Unit testing |

Then create an activity list table that includes:

- Activity ID: a unique identifier for each activity.

- Activity Name: descriptive and verb-oriented.

- Related WBS ID: reference the corresponding WBS element.

- Description: brief explanation of the activity.

- Estimated Duration:provide a time estimate for each activity using a consistent unit (hours, days, or weeks). All activities must use the same unit.

Tip: Be precise and realistic with durations; avoid vague estimates like “short” or “long.”

Activity List is a compilation of all activities to be included in the project schedule.

Each activity includes the activity name, unique identifier or number, and a brief description.

Activity attributes provide additional details about the activity:

- Predecessors and successors.

- Logical relationships between activities.

- Leads and lags.

- Resource requirements.

- Constraints and imposed dates.

- Assumptions related to the activity. Both need to match the WBS and WBS dictionary and be examined by key project stakeholders.

| WBS ID | WBS Item | Description | Resources Needed | Dependencies | Activities |
| --- | --- | --- | --- | --- | --- |
| 1.1.1 | Storyboard | Structured outline of the game’s narrative progression, including major plot points, branching paths, and alternative endings | Storyboarding software or document editor, narrative planning sessions | None (foundation for narrative system) | Storyboard and theme conceptualization |
| 1.1.2 | Character Design Documents | Comprehensive document detailing each character’s name, personality traits, backstory, motivations, relationships, and narrative role | Storyboarding software or document editor, narrative planning sessions | Storyboard (1.1.1) | Determine characters (playable and non-playable) and their character arcs |
| 1.1.3 | Dialogue Scripts | Written dialogue lines for characters, including fixed scripted dialogue and reference lines for LLM-generated content alignment | Script writing software or document editor, narrative writing sessions | Storyboard (1.1.1), Character Design Documents (1.1.2) | Write dialogue graphs and conditions |
| 1.2.1 | UI Design | Complete visual layout designs for menus, chat interfaces, and player input displays | UI/UX design software (e.g., Figma), design guidelines | User Interfaces (1.6) | Conceptualize the artistic side of the user interface |
| 1.2.2 | Voice Assets | Voice lines to accompany dialogue from within the game | Microphone, recording software, audio editing tools, Text-to-speech tools, LLM outputs, audio processing software | Dialogue Scripts (1.1.3), Response Processor (1.4.2.2) |  |
| 1.2.2.1 | Human Voice Assets | Recorded and edited human voice lines for characters, formatted for Unity integration | Microphone, recording software, audio editing tools | Dialogue Scripts (1.1.3) | Record and edit voice lines based on the dialogue scripts |
| 1.2.2.2 | LLM Voice Assets | Generated and processed synthetic voice outputs corresponding to LLM-generated dialogue | Text-to-speech tools, LLM outputs, audio processing software | Response Processor (1.4.2.2) | Prompt LLM for voice assets, import and edit to align with human voice assets |
| 1.2.3 | Character Artworks | Character visual assets formatted for integration into Unity | Digital illustration software (e.g., Procreate, Photoshop), graphic design tools | Character Design Documents (1.1.2) | Create conceptual artwork for designed characters based on 1.1.2 |
| 1.2.4 | Background Music | Collection of background music tracks assigned to narrative states and gameplay events | Music composition software or royalty-free music libraries, audio editing tools | Storyboard (1.1.1) | Searching for non-copyright background music and sfx |
| 1.3.1 | Unity Project Folder | Configured Unity project environment containing game scenes, scripts, assets, and project settings | Unity Engine, version control system (e.g., Git), development environment | Dialogue Scripts (1.1.3), Audio and Visual Assets (1.2), LLM Integration (1.4), Gameplay Mechanics (1.5) | Continuously package all elements into a single exportable folder for users to download |
| 1.4.1 | LLM API Integration Module | Implementation of secure API calls to the selected LLM service, including authentication and request handling | LLM API access, Unity scripting (C#), API documentation | Unity Project Folder (1.3.1) | Compare LLMs to decide which is the best for our use, get an API key, implement secure calls (authentication and request handling) |
| 1.4.2 | Dialogue Generation System | System for using the selected LLM to generate character dialogue for use within the game | LLM testing environment, narrative documentation, Unity scripting environment, LLM API responses | Narrative System (1.1) |  |
| 1.4.2.1 | Prompt Template | Structured prompt templates defining personality, context, and dialogue constraints for generating character responses | LLM testing environment, narrative documentation | Narrative System (1.1), LLM API Integration Module (1.4.1), Prompt Template (1.4.2.1) | Create prompt templates for each character (include personality, context and dialogue constraints) to generate character dialogue using few-shot/chain-of-thought prompting |
| 1.4.2.2 | Response Processor | Script that parses, filters, and formats LLM responses for in-game display | Unity scripting environment, LLM API responses | LLM API Integration Module (1.4.1), Prompt Template (1.4.2.1) | Create a script that reliably parses LLM responses for in-game display |
| 1.4.3 | Context Memory Manager | System for tracking and injecting relevant game state and conversation history into LLM prompts | Unity scripting environment, data storage structures | Narrative System (1.1), LLM API Integration Module (1.4.1), Gameplay Mechanics (1.5), | Divide LLM prompts into pre-prompted/stored and runtime-prompted, |
| 1.5.1 | Game State Controller | Central controller managing scene transitions, narrative states, and gameplay progression | Unity scripting environment, state management logic | Unity Project Folder (1.3.1) | Create scripts controlling game state (menu, in-game, etc.) and integrate with 1.5.2 |
| 1.5.2 | Choice Tracking System | Module for recording and processing player decisions to influence narrative outcomes | Unity scripting, data storage structures | Dialogue Scripts (1.1.3) | Determine logical and gameplay conditions that lead to dialogue branches and implement in script |
| 1.5.3 | Game Persistence System | System for ensuing game states can persist through the saving and loading of a playthrough, as well as the opening and closing of the game | Device storage access | Game State Controller (1.5.1), Choice Tracking System (1.5.2) |  |
| 1.5.3.1 | Save System | System for ensuring all player game states and settings are saved | Device storage access, Device storage, Database access | Game State Controller (1.5.1), Choice Tracking System (1.5.2) | Save state in local Appdata, can use unity in built save system |
| 1.5.3.2 | Load System | System for ensuring all player game states and settings are successfully loaded, allowing seamless continued gameplay | Device storage access | Game State Controller (1.5.1), Choice Tracking System (1.5.2) | Load game state if player decides to stop playthrough midway and comes back to play it |
| 1.6.1 | Menus | UI components for allowing players to move between certain game states and change settings | Unity UI tools | Game State Controller (1.5.1) | Implementation of 1.2.1 for menus, implement backend API to detect input |
| 1.6.2 | Chat Display | UI component for displaying scripted and LLM-generated dialogue in real time | Unity UI tools | Dialogue Scripts (1.1.3), Response Processor (1.4.2.2) | Implementation of 1.2.1 for chat display |
| 1.6.3 | Player Input Display | UI component allowing players to input dialogue responses or choices | Unity UI tools | Dialogue Scripts (1.1.3), Chat Display (1.6.2) | Implementation of 1.2.1 for player input display, implement backend API |
| 1.7.1 | Technical Documentation | Documentation of the game’s design and operative protocols, as well as its historical progress | Documentation tools, diagramming tools, version control system | Completion of project |  |
| 1.7.1.1 | System Architecture Document | Technical document outlining system components, architecture diagrams, and module interactions | Diagramming tools (e.g., draw.io, astah) | Completion of system design modules | Design UML class diagram and state transition diagram. |
| 1.7.1.2 | API Document | Documentation describing API endpoints, request/response formats, and integration procedures | Documentation tools | LLM API Integration Module (1.4.1) | Create an organized document detailing the process of implementing the API endpoints, request/response formats, and integration procedures |
| 1.7.1.3 | Version Control System | System for documenting different iterations of project progress in both design and implementation | Documentation tools (e.g., Google Docs), version control system (e.g., Git) | None (can document project progress immediately) | Document changes to project and track commits and PRs using git, track potential changes and ideas in google docs |
| 1.7.2 | Player Documentation | Documentation intended to assist players with experiencing the game | Documentation tools | Unity Project Folder (1.3.1) |  |
| 1.7.2.1 | Installation & Setup Guide | Instructions for installing, configuring, and running the Unity game | Documentation tools, Unity Engine | Narrative System (1.1), Unity Project Folder (1.3.1), Gameplay Mechanics (1.5), User Interfaces (1.6) | Create a document that details the instructions for installing, configuring, and running the Unity game |
| 1.7.2.2 | Player Guide | User manual explaining gameplay mechanics, controls, and objectives | Documentation tools | Narrative System (1.1), Gameplay Mechanics (1.5), User Interfaces (1.6) | Create a document explaining gameplay mechanics, controls, and objectives (user manual) |

| Activity ID | Activity Name | Related WBS ID | Description | Estimated Duration (hours) | Dependent On |
| --- | --- | --- | --- | --- | --- |
| WBS1.1.1-A1 | Storyboard | 1.1.1 | Theme conceptualization | 48 |  |
| WBS1.1.1-A2 | Storyboard | 1.1.1 | Story conceptualization | 48 | WBS1.1.1-A1 |
| WBS1.1.2-A1 | Character Design Documents | 1.1.2 | Determine characters’ names. | 28 | WBS1.1.1-A2 |
| WBS1.1.2-A2 | Character Design Documents | 1.1.2 | Determine characters’ personalities and motives. | 48 | WBS1.1.2-A1 |
| WBS1.1.2-A3 | Character Design Documents | 1.1.2 | Determine characters’ roles and/or development throughout the story. | 58 | WBS1.1.2-A2 |
| WBS1.1.3-A1 | Dialogue Scripts | 1.1.3 | Write narration/main character scripts to solidify the direction of the story. This includes the beginning of the story and the initial world building that follows. | 62 | WBS1.1.2-A1 |
| WBS1.1.3-A2 | Dialogue Scripts | 1.1.3 | Write scripts for the interactions between the main character and each of the supporting characters. | 62 | WBS1.1.2-A2 |
| WBS1.1.3-A3 | Dialogue Scripts | 1.1.3 | Establish conditional dialogue pathways based on what the main character has chosen to talk about with each supporting character. | 72 | WBS1.1.2-A3 |
| WBS1.1.3-A4 | Dialogue Scripts | 1.1.3 | Create dialogue graphs for the interactions between the main character and each of the supporting characters. These will visualize the logic of the game. | 104 | WBS1.1.3-A2 WBS1.1.3-A3 |
| WBS1.2.1-A1 | UI Design | 1.2.1 | Conceptualize the visual theme of the game. This takes into account story elements like theme, mood, setting, etc. This includes colours, shapes, textures, etc. | 60 | WBS1.1.1-A2 |
| WBS1.2.1-A2 | UI Design | 1.2.1 | Conceptualize the visual design of the user interface. This includes design for the main menu, new game creation menu, in-game menu, settings, in-game narration, in-game conversation, and in-game dialogue options. | 46 | WBS1.2.1-A1 |
| WBS1.2.1-A3 | UI Design | 1.2.1 | Create the visual assets for each interface. | 46 | WBS1.2.1-A2 |
| WBS1.2.2-A1 | Voice Effects | 1.2.2 | Search and select non-copyright sound effects for text that will show up on the screen. | 24 | WBS1.1.3-A1 |
| WBS1.2.3-A1 | Character Artwork | 1.2.3 | Create artwork for each character based on the character design documents. | 70 | WBS1.1.2-A3 |
| WBS1.2.4-A1 | Background Music | 1.2.4 | Conceptualize the auditory theme of the game. This takes into account story elements like theme, mood, setting, etc. This includes rhythm, tempo, melody, etc. | 74 | WBS1.1.1-A2 |
| WBS1.2.4-A2 | Background Music | 1.2.4 | Search and select non-copyright music that matches the chosen theme. | 22 | WBS1.2.4-A1 |
| WBS1.2.4-A3 | Background Music | 1.2.4 | Search and select non-copyright sound effects for enhancing story telling. | 22 | WBS1.2.4-A2 |
| WBS1.2.4-A4 | Background Music | 1.2.4 | Search and select non-copyright sound effects for interacting with UI elements. | 22 | WBS1.2.4-A3 |
| WBS1.3.1-A1 | Unity Project Folder | 1.3.1 | Organize and package all game assets and scripts into a single exportable folder for users to download. | 36 | WBS1.1.3-A4, WBS1.2.1-A3, WBS1.2.3-A1, WBS1.2.4-A4 WBS1.2.2-A1 |
| WBS1.4.1-A1 | LLM API Integration Module | 1.4.1 | Compare different LLMs and decide which is best for our use. | 70 | WBS1.3.1-A1 |
| WBS1.4.1-A2 | LLM API Integration Module | 1.4.1 | Obtain an API key for the selected LLM. | 38 | WBS1.4.1-A1 |
| WBS1.4.1-A3 | LLM API Integration Module | 1.4.1 | Implement secure API calls in the game. This includes authentication and request handling. | 38 | WBS1.4.1-A2 |
| WBS1.4.2.1-A1 | Prompt Template | 1.4.2.1 | Create prompt templates for each character. This includes details about their personality, narrative context, and dialogue constraints. | 64 | WBS1.1.3-A3 |
| WBS1.4.2.1-A2 | Prompt Template | 1.4.2.1 | Generate the character dialogue through API calls using few-shot or chain-of-thought prompting. | 92 | WBS1.4.2.1-A1 |
| WBS1.4.2.2-A1 | Response Processor | 1.4.2.2 | Create a script that reliably parses LLM responses for in-game display. | 56 | WBS1.4.2.1-A2 |
| WBS1.4.2.2-A2 | Response Processor | 1.4.2.2 | Create a script for integrating processed LLM responses into the game, so that they can be displayed. | 64 | WBS1.4.2.2-A1 |
| WBS1.4.3-A1 | Context Memory Manager | 1.4.3 | Divide LLM prompts into pre-prompted/stored and runtime-prompted. | 58 | WBS1.4.2.2-A2 |
| WBS1.4.3-A2 | Context Memory Manager | 1.4.3 | Use LangChain to help manage context for the LLM. | 36 | WBS1.4.3-A1 |
| WBS1.5.1-A1 | Game State Controller | 1.5.1 | Create scripts to control the game state. | 48 | WBS1.3.1-A1 |
| WBS1.5.1-A2 | Game State Controller | 1.5.1 | Integrate game state controllers with the choice tracking system. | 14 | WBS1.5.1-A1 |
| WBS1.5.2-A1 | Choice Tracking System | 1.5.2 | Determine logical gameplay conditions that lead to dialogue branches. | 50 | WBS1.1.3-A4 |
| WBS1.5.2-A2 | Choice Tracking System | 1.5.2 | Implement the decided conditions within the game. | 58 | WBS1.5.2-A1 |
| WBS1.5.3.1-A1 | Save System | 1.5.3.1 | Save game state in local Appdata using the Unity built-in save system. | 14 | WBS1.5.1-A1 |
| WBS1.5.3.2-A1 | Load System | 1.5.3.2 | Load game state from local Appdata using the Unity built-in save system. | 14 | WBS1.5.3.1-A1 |
| WBS1.6.1-A1 | Menus | 1.6.1 | Implement menus to be used within the game. This is based on the UI design created for them. | 14 | WBS1.2.1-A3 |
| WBS1.6.1-A2 | Menus | 1.6.1 | Create scripts to detect player input and change the game state accordingly. This is for interacting with menus. | 16 | WBS1.6.1-A1 |
| WBS1.6.2-A1 | Chat Display | 1.6.2 | Implement the chat interface to visually display dialogue between characters. This is based on the UI design created for it. | 14 | WBS1.2.1-A3 |
| WBS1.6.3-A1 | Player Input Display | 1.6.3 | Implement the interface for selecting player responses. This is based on the UI design created for it. | 14 | WBS1.2.1-A3 |
| WBS1.6.3-A2 | Player Input Display | 1.6.3 | Create scripts to detect player input and change the game state accordingly. This is for interacting with player responses. | 60 | WBS1.6.3-A1 |
| WBS1.7.1.1-A1 | System Architecture Document | 1.7.1.1 | Design UML class diagram to include relevant classes created in C# scripts. | 36 | WBS1.4.3-A2 WBS1.5.3-A1 WBS1.5.1-A2 WBS1.5.2-A2 WBS1.6.1-A2 WBS1.6.2-A1 WBS1.6.3-A2 WBS1.7.1.2-A1 |
| WBS1.7.1.1-A2 | System Architecture Document | 1.7.1.1 | Create the state transition diagram describing overarching game states such as in-menu, in-game, etc. | 14 | WBS1.4.3-A2 WBS1.5.3-A1 WBS1.5.1-A2 WBS1.5.2-A2 WBS1.6.1-A2 WBS1.6.2-A1 WBS1.6.3-A2 WBS1.7.1.2-A1 |
| WBS1.7.1.2-A1 | API Document | 1.7.1.2 | Create an organized document to detail API usage. | 24 | WBS1.4.1-A3 |
| WBS1.7.1.2-A2 | API Document | 1.7.1.2 | Describe the process to implement the API endpoints, request/response formats, and integration procedures. | 24 | WBS1.7.1.2-A1 |
| WBS1.7.1.3-A1 | Version Control System | 1.7.1.3 | During development, track all code changes using GitHub. | 84 | WBS1.7.1.1-A1 WBS1.7.1.1-A2 |
| WBS1.7.1.3-A2 | Version Control System | 1.7.1.3 | During development, track all potential and real design changes using Google Docs. | 48 | WBS1.7.1.1-A1 WBS1.7.1.1-A2 |
| WBS1.7.2.1-A1 | Installation & Setup Guide | 1.7.2.1 | Describe the installation process. This includes how to download all needed files for the game to function. | 14 | WBS1.7.1.3-A1 WBS1.7.1.3-A2 |
| WBS1.7.2.1-A2 | Installation & Setup Guide | 1.7.2.1 | Describe some troubleshooting advice in case of some common errors. | 14 | WBS1.7.1.3-A1 WBS1.7.1.3-A2 |
| WBS1.7.2.1-A3 | Installation & Setup Guide | 1.7.2.1 | Describe instructions to configure and run the game. This includes how to run the game’s executable file, how to adjust settings, how to turn off additional LLM generation, and how to save and load a game. | 14 | WBS1.7.1.3-A1 WBS1.7.1.3-A2 |
| WBS1.7.2.2-A1 | Player Guide | 1.7.2.2 | Create a document explaining gameplay goals, mechanics, and controls. This will be a user manual players can refer to for playing the game. | 38 | WBS1.7.1.3-A1 WBS1.7.1.3-A2 |

# Part 2: Network Diagram and Critical Path

# Part 2: Network Diagram and Critical Path

- Using your activity list table, create a Network Diagram that clearly shows:

- Dependencies between activities

- Duration of each activity.

- Identify the Critical Path, which is the sequence of activities that determines the shortest project duration.

- Calculate the Total Project Duration based on the critical path.

Ensure your network diagram is neat and readable.

Critical Path : 1 - 2 - 3 - 6 - 9 - 11 - 13 - 14 - 17 - 23 - 24 - 27 - 31 - 32 - 33 - 34

Total Project Duration = 730 hours ≈ 30 days