## HourCalc
Activity ID | Description | Optimistic | Most Likely | Pessimistic | PERT
WBS1.1.1-A1 | Theme conceptualization | 2 | 4 | 6 | 4
WBS1.1.1-A2 | Story conceptualization | 2 | 4 | 6 | 4
WBS1.1.2-A1 | Determine characters’ names. | 1 | 2 | 5 | 2.3333
WBS1.1.2-A2 | Determine characters’ personalities and motives. | 3 | 4 | 5 | 4
WBS1.1.2-A3 | Determine characters’ roles and/or development throughout the story. | 3 | 5 | 6 | 4.8333
WBS1.1.3-A1 | Write narration/main character scripts to solidify the direction of the story. This includes the beginning of the story and the initial world building that follows. | 4 | 5 | 7 | 5.1667
WBS1.1.3-A2 | Write scripts for the interactions between the main character and each of the supporting characters. | 4 | 5 | 7 | 5.1667
WBS1.1.3-A3 | Establish conditional dialogue pathways based on what the main character has chosen to talk about with each supporting character. | 5 | 6 | 7 | 6
WBS1.1.3-A4 | Create dialogue graphs for the interactions between the main character and each of the supporting characters. These will visualize the logic of the game. | 7 | 9 | 9 | 8.6667
WBS1.2.1-A1 | Conceptualize the visual theme of the game. This takes into account story elements like theme, mood, setting, etc. This includes colours, shapes, textures, etc. | 4 | 5 | 6 | 5
WBS1.2.1-A2 | Conceptualize the visual design of the user interface. This includes design for the main menu, new game creation menu, in-game menu, settings, in-game narration, in-game conversation, and in-game dialogue options. | 3 | 4 | 4 | 3.8333
WBS1.2.1-A3 | Create the visual assets for each interface. | 3 | 4 | 4 | 3.8333
WBS1.2.2-A1 | Search and select non-copyright sound effects for text that will show up on the screen. | 1 | 2 | 3 | 2
WBS1.2.3-A1 | Create artwork for each character based on the character design documents. | 5 | 6 | 6 | 5.8333
WBS1.2.4-A1 | Conceptualize the auditory theme of the game. This takes into account story elements like theme, mood, setting, etc. This includes rhythm, tempo, melody, etc. | 5 | 6 | 8 | 6.1667
WBS1.2.4-A2 | Search and select non-copyright music that matches the chosen theme. | 1 | 2 | 2 | 1.8333
WBS1.2.4-A3 | Search and select non-copyright sound effects for enhancing story telling. | 1 | 2 | 2 | 1.8333
WBS1.2.4-A4 | Search and select non-copyright sound effects for interacting with UI elements. | 1 | 2 | 2 | 1.8333
WBS1.3.1-A1 | Organize and package all game assets and scripts into a single exportable folder for users to download. | 2 | 3 | 4 | 3
WBS1.4.1-A1 | Compare different LLMs and decide which is best for our use. | 5 | 6 | 6 | 5.8333
WBS1.4.1-A2 | Obtain an API key for the selected LLM. | 3 | 3 | 4 | 3.1667
WBS1.4.1-A3 | Implement secure API calls in the game. This includes authentication and request handling. | 3 | 3 | 4 | 3.1667
WBS1.4.2.1-A1 | Create prompt templates for each character. This includes details about their personality, narrative context, and dialogue constraints. | 5 | 5 | 7 | 5.3333
WBS1.4.2.1-A2 | Generate the character dialogue through API calls using few-shot or chain-of-thought prompting. | 6 | 8 | 8 | 7.6667
WBS1.4.2.2-A1 | Create a script that reliably parses LLM responses for in-game display. | 3 | 5 | 5 | 4.6667
WBS1.4.2.2-A2 | Create a script for integrating processed LLM responses into the game, so that they can be displayed. | 5 | 5 | 7 | 5.3333
WBS1.4.3-A1 | Divide LLM prompts into pre-prompted/stored and runtime-prompted. | 4 | 5 | 5 | 4.8333
WBS1.4.3-A2 | Use LangChain to help manage context for the LLM. | 1 | 3 | 5 | 3
WBS1.5.1-A1 | Create scripts to control the game state. | 3 | 4 | 5 | 4
WBS1.5.1-A2 | Integrate game state controllers with the choice tracking system. | 1 | 1 | 2 | 1.1667
WBS1.5.2-A1 | Determine logical gameplay conditions that lead to dialogue branches. | 3 | 4 | 6 | 4.1667
WBS1.5.2-A2 | Implement the decided conditions within the game. | 3 | 5 | 6 | 4.8333
WBS1.5.3.1-A1 | Save game state in local Appdata using the Unity built-in save system. | 1 | 1 | 2 | 1.1667
WBS1.5.3.2-A1 | Load game state from local Appdata using the Unity built-in save system. | 1 | 1 | 2 | 1.1667
WBS1.6.1-A1 | Implement menus to be used within the game. This is based on the UI design created for them. | 1 | 1 | 2 | 1.1667
WBS1.6.1-A2 | Create scripts to detect player input and change the game state accordingly. | 1 | 1 | 3 | 1.3333
WBS1.6.2-A1 | Implement the chat interface to visually display dialogue between characters. This is based on the UI design created for it. | 1 | 1 | 2 | 1.1667
WBS1.6.3-A1 | Implement the interface for selecting player responses. This is based on the UI design created for it. | 1 | 1 | 2 | 1.1667
WBS1.6.3-A2 | Create scripts to detect player input and change the game state accordingly. | 3 | 5 | 7 | 5
WBS1.7.1.1-A1 | Design UML class diagram to include relevant classes created in C# scripts. | 1 | 3 | 5 | 3
WBS1.7.1.1-A2 | Create the state transition diagram describing overarching game states such as in-menu, in-game, etc. | 1 | 1 | 2 | 1.1667
WBS1.7.1.2-A1 | Create an organized document to detail API usage. | 1 | 2 | 3 | 2
WBS1.7.1.2-A2 | Describe the process to implement the API endpoints, request/response formats, and integration procedures. | 1 | 2 | 3 | 2
WBS1.7.1.3-A1 | During development, track all code changes using GitHub. | 7 | 7 | 7 | 7
WBS1.7.1.3-A2 | During development, track all potential and real design changes using Google Docs. | 3 | 4 | 5 | 4
WBS1.7.2.1-A1 | Describe the installation process. This includes how to download all needed files for the game to function. | 1 | 1 | 2 | 1.1667
WBS1.7.2.1-A2 | Describe some troubleshooting advice in case of some common errors. | 1 | 1 | 2 | 1.1667
WBS1.7.2.1-A3 | Describe instructions to configure and run the game. This includes how to run the game’s executable file, how to adjust settings, how to turn off additional LLM generation, and how to save and load a game. | 1 | 1 | 2 | 1.1667
WBS1.7.2.2-A1 | Create a document explaining gameplay goals, mechanics, and controls. This will be a user manual players can refer to for playing the game. | 2 | 3 | 5 | 3.1667

## ActID
WBS ID | WBS Name | Activity ID | Activity Name | Activity Desc. | Duration(Days) | Duration (Hours) | Dependent On
1.1.1 | Storyboard | WBS1.1.1-A1 | Storyboard - Theme | Theme conceptualization | 4 | 48
|  | WBS1.1.1-A2 | Storyboard - Story | Story conceptualization | 4 | 48 | WBS1.1.1-A1
1.1.2 | Character Design Documents | WBS1.1.2-A1 | Character Design - Names | Determine characters’ names. | 2.3333 | 28 | WBS1.1.1-A2
|  | WBS1.1.2-A2 | Character Design - Personalities | Determine characters’ personalities and motives. | 4 | 48 | WBS1.1.2-A1
|  | WBS1.1.2-A3 | Character Design - Narrative Roles | Determine characters’ roles and/or development throughout the story. | 4.8333 | 58 | WBS1.1.2-A2
1.1.3 | Dialogue Scripts | WBS1.1.3-A1 | Dialogue Scripts - Beginning | Write narration/main character scripts to solidify the direction of the story. This includes the beginning of the story and the initial world building that follows. | 5.1667 | 62 | WBS1.1.2-A1
|  | WBS1.1.3-A2 | Dialogue Scripts - Characters | Write scripts for the interactions between the main character and each of the supporting characters. | 5.1667 | 62 | WBS1.1.2-A2
|  | WBS1.1.3-A3 | Dialogue Scripts - Conditional Paths | Establish conditional dialogue pathways based on what the main character has chosen to talk about with each supporting character. | 6 | 72 | WBS1.1.2-A3
|  | WBS1.1.3-A4 | Dialogue Scripts - Graphs | Create dialogue graphs for the interactions between the main character and each of the supporting characters. These will visualize the logic of the game. | 8.6667 | 104 | WBS1.1.3-A2 WBS1.1.3-A3
1.2.1 | UI Design | WBS1.2.1-A1 | UI Design - Theme | Conceptualize the visual theme of the game. This takes into account story elements like theme, mood, setting, etc. This includes colours, shapes, textures, etc. | 5 | 60 | WBS1.1.1-A2
|  | WBS1.2.1-A2 | UI Design - Visuals | Conceptualize the visual design of the user interface. This includes design for the main menu, new game creation menu, in-game menu, settings, in-game narration, in-game conversation, and in-game dialogue options. | 3.8333 | 46 | WBS1.2.1-A1
|  | WBS1.2.1-A3 | UI Design - Assets | Create the visual assets for each interface. | 3.8333 | 46 | WBS1.2.1-A2
1.2.2 | Voice Effects | WBS1.2.2-A1 | Voice Effects | Search and select non-copyright sound effects for text that will show up on the screen. | 2 | 24 | WBS1.1.3-A1
1.2.3 | Character Artwork | WBS1.2.3-A1 | Character Artwork | Create artwork for each character based on the character design documents. | 5.8333 | 70 | WBS1.1.2-A3
1.2.4 | Background Music | WBS1.2.4-A1 | Background Music - Theme | Conceptualize the auditory theme of the game. This takes into account story elements like theme, mood, setting, etc. This includes rhythm, tempo, melody, etc. | 6.1667 | 74 | WBS1.1.1-A2
|  | WBS1.2.4-A2 | Background Music - Select BGM | Search and select non-copyright music that matches the chosen theme. | 1.8333 | 22 | WBS1.2.4-A1
|  | WBS1.2.4-A3 | Background Music - Select Story SFX | Search and select non-copyright sound effects for enhancing story telling. | 1.8333 | 22 | WBS1.2.4-A2
|  | WBS1.2.4-A4 | Background Music - Select UI SFX | Search and select non-copyright sound effects for interacting with UI elements. | 1.8333 | 22 | WBS1.2.4-A3
1.3.1 | Unity Project Folder | WBS1.3.1-A1 | Unity Project Folder | Organize and package all game assets and scripts into a single exportable folder for users to download. | 3 | 36 | WBS1.1.3-A4, WBS1.2.1-A3, WBS1.2.3-A1, WBS1.2.4-A4 WBS1.2.2-A1
1.4.1 | LLM API Integration Module | WBS1.4.1-A1 | LLM API Integration Module - LLM Comparison | Compare different LLMs and decide which is best for our use. | 5.8333 | 70 | WBS1.3.1-A1
|  | WBS1.4.1-A2 | LLM API Integration Module -API Key | Obtain an API key for the selected LLM. | 3.1667 | 38 | WBS1.4.1-A1
|  | WBS1.4.1-A3 | LLM API Integration Module - API Calls | Implement secure API calls in the game. This includes authentication and request handling. | 3.1667 | 38 | WBS1.4.1-A2
1.4.2.1 | Prompt Template | WBS1.4.2.1-A1 | Prompt Template - Characters | Create prompt templates for each character. This includes details about their personality, narrative context, and dialogue constraints. | 5.3333 | 64 | WBS1.1.3-A3
|  | WBS1.4.2.1-A2 | Prompt Template - Generate | Generate the character dialogue through API calls using few-shot or chain-of-thought prompting. | 7.6667 | 92 | WBS1.4.2.1-A1
1.4.2.2 | Response Processor | WBS1.4.2.2-A1 | Response Processor - Parse Dialogue | Create a script that reliably parses LLM responses for in-game display. | 4.6667 | 56 | WBS1.4.2.1-A2
|  | WBS1.4.2.2-A2 | Response Processor - Game Integration | Create a script for integrating processed LLM responses into the game, so that they can be displayed. | 5.3333 | 64 | WBS1.4.2.2-A1
1.4.3 | Context Memory Manager | WBS1.4.3-A1 | Context Memory Manager - Separation | Divide LLM prompts into pre-prompted/stored and runtime-prompted. | 4.8333 | 58 | WBS1.4.2.2-A2
|  | WBS1.4.3-A2 | Context Memory Manager - LangChain | Use LangChain to help manage context for the LLM. | 3 | 36 | WBS1.4.3-A1
1.5.1 | Game State Controller | WBS1.5.1-A1 | Game State Controller - Scripts | Create scripts to control the game state. | 4 | 48 | WBS1.3.1-A1
|  | WBS1.5.1-A2 | Game State Controller - Choice Integration | Integrate game state controllers with the choice tracking system. | 1.1667 | 14 | WBS1.5.1-A1
1.5.2 | Choice Tracking System | WBS1.5.2-A1 | Choice Tracking System - Gameplay Conditions | Determine logical gameplay conditions that lead to dialogue branches. | 4.1667 | 50 | WBS1.1.3-A4
|  | WBS1.5.2-A2 | Choice Tracking System - Implementation | Implement the decided conditions within the game. | 4.8333 | 58 | WBS1.5.2-A1
1.5.3.1 | Save System | WBS1.5.3.1-A1 | Save System | Save game state in local Appdata using the Unity built-in save system. | 1.1667 | 14 | WBS1.5.1-A1
1.5.3.2 | Load System | WBS1.5.3.2-A1 | Load System | Load game state from local Appdata using the Unity built-in save system. | 1.1667 | 14 | WBS1.5.3.1-A1
1.6.1 | Menus | WBS1.6.1-A1 | Menus - Implementation | Implement menus to be used within the game. This is based on the UI design created for them. | 1.1667 | 14 | WBS1.2.1-A3
|  | WBS1.6.1-A2 | Menus - Game State | Create scripts to detect player input and change the game state accordingly. This is for interacting with menus. | 1.3333 | 16 | WBS1.6.1-A1
1.6.2 | Chat Display | WBS1.6.2-A1 | Chat Display | Implement the chat interface to visually display dialogue between characters. This is based on the UI design created for it. | 1.1667 | 14 | WBS1.2.1-A3
1.6.3 | Player Input Display | WBS1.6.3-A1 | Player Input Display - Implementation | Implement the interface for selecting player responses. This is based on the UI design created for it. | 1.1667 | 14 | WBS1.2.1-A3
|  | WBS1.6.3-A2 | Player Input Display - Game State | Create scripts to detect player input and change the game state accordingly. This is for interacting with player responses. | 5 | 60 | WBS1.6.3-A1
1.7.1.1 | System Architecture Document | WBS1.7.1.1-A1 | System Architecture Document - UML Diagrams | Design UML class diagram to include relevant classes created in C# scripts. | 3 | 36 | WBS1.4.3-A2 WBS1.5.3-A1 WBS1.5.1-A2 WBS1.5.2-A2 WBS1.6.1-A2 WBS1.6.2-A1 WBS1.6.3-A2 WBS1.7.1.2-A1
|  | WBS1.7.1.1-A2 | System Architecture Document - State Transition Diagrams | Create the state transition diagram describing overarching game states such as in-menu, in-game, etc. | 1.1667 | 14 | WBS1.4.3-A2 WBS1.5.3-A1 WBS1.5.1-A2 WBS1.5.2-A2 WBS1.6.1-A2 WBS1.6.2-A1 WBS1.6.3-A2 WBS1.7.1.2-A1
1.7.1.2 | API Document | WBS1.7.1.2-A1 | API Document - Usage | Create an organized document to detail API usage. | 2 | 24 | WBS1.4.1-A3
|  | WBS1.7.1.2-A2 | API Document - Endpoints | Describe the process to implement the API endpoints, request/response formats, and integration procedures. | 2 | 24 | WBS1.7.1.2-A1
1.7.1.3 | Version Control System | WBS1.7.1.3-A1 | Version Control System - GitHub | During development, track all code changes using GitHub. | 7 | 84 | WBS1.7.1.1-A1 WBS1.7.1.1-A2
|  | WBS1.7.1.3-A2 | Version Control System - Google Docs | During development, track all potential and real design changes using Google Docs. | 4 | 48 | WBS1.7.1.1-A1 WBS1.7.1.1-A2
1.7.2.1 | Installation & Setup Guide | WBS1.7.2.1-A1 | Installation & Setup Guide - Download Process | Describe the installation process. This includes how to download all needed files for the game to function. | 1.1667 | 14 | WBS1.7.1.3-A1 WBS1.7.1.3-A2
|  | WBS1.7.2.1-A2 | Installation & Setup Guide - Troubleshooting | Describe some troubleshooting advice in case of some common errors. | 1.1667 | 14 | WBS1.7.1.3-A1 WBS1.7.1.3-A2
|  | WBS1.7.2.1-A3 | Installation & Setup Guide - Configuration | Describe instructions to configure and run the game. This includes how to run the game’s executable file, how to adjust settings, how to turn off additional LLM generation, and how to save and load a game. | 1.1667 | 14 | WBS1.7.1.3-A1 WBS1.7.1.3-A2
1.7.2.2 | Player Guide | WBS1.7.2.2-A1 | Player Guide | Create a document explaining gameplay goals, mechanics, and controls. This will be a user manual players can refer to for playing the game. | 3.1667 | 38 | WBS1.7.1.3-A1 WBS1.7.1.3-A2

## Sheet3
Character Sheet Template
Name: | Scarlett Vane | Character Render | Personality Traits
Physical Traits |  |  | Type | Bold, confident, kick boxer
Gender | Female | Independent, self-reliant, | Likes | rock music, motorcycle
Hair Colour | long ponytail red hair | sharp thinker, high self-confident | Dislikes | lier, not confident people,
stupidity
Eye Colour | Blue |  | Social Stance | Don't talk that much, perfectionlist,
Build | athletic |  |  | talk logically, single, solo traveling
Height | 5'8 |  | Political Stance | fights for freedom, anti-establishmet,
Weight | 60 kg
Extra | fair skin, multiple ear piercing,
wears leather jackets, ripped
jeans, white tank top,
natural look, early thirties
Character Sheet Template
Name: | David Johnson | Character Render | Personality Traits
Physical Traits |  | Moves deliberately, | Type | Logical, analytical, strategic, enthusisastic
Gender | Male | gives impression of intelligence, | Likes | Planning, solving complex problems,
reading, physics research
Hair Colour | brown | Guides team using logic and strategy | Dislikes
Eye Colour | brown |  | Social Stance | Calm, patience, values other peoples
Build | Toned body |  |  | opinion, respectful
Height | 6'1 |  | Political Stance | High observation skill, good prediction,
Weight | 75kg |  |  | calculate risk effectively
Extra | Wears glasses, late twenties,
handsome, casual clothing, shirt
and pant, white
Character Sheet Template
Name: | Nico Takahashi | Character Render | Personality Traits
Physical Traits |  |  | Type | Lazy, game addict, hate school
Gender | Male |  | Likes | video games, coding, techy
Hair Colour | black | Teen hacker, laid-back but sharp, tech-savvy | Dislikes | social commitment, hate alomost everybody
Eye Colour | dark - brown |  | Social Stance | Introverted, prefers minimal interaction
Build | lean | Expert in coding, hacking, |  | distance but notices everything,
Height | 6'0 | and manipulating digital systems | Political Stance | Doesn’t care about politics,
Weight | 70kg |  |  | No personal opinion
Extra | Asian-american, baggy clothing, | Observes AI and security patterns carefully before acting
genz, were loose t shirt and shorts
Teenage like 19-20
always have headset
Character Sheet Template
Name: | Maya Rodriguez | Character Render | Personality Traits
Physical Traits |  |  | Type | Innocent, timid, scard, shy
Gender | Female | Soft-spoken boanist and florist, gentle, god fear | Likes | Flowers, plants, gardening, nature, cooking, married
Hair Colour | black curly hair | Round face, freckles, always simile | Dislikes | Conflict, loud people, stressful situations
Eye Colour | brown | Very trusting, easily influenced by others | Social Stance | Good at socializing, positive thinking, friendly, kind
Build | chubby
Height | 5'5 |  | Political Stance
Weight | 85kg |  |  | No strong opinions, tends to believe what others say
Extra | Age 38-45, soft-spoken, wears
sweater skirt
Character Sheet Template
Name: | Aiden Miller | Character Render | Personality Traits
Physical Traits |  | Former soldier with a hardened, intimidating presence, short hair, disciplined posture, wear combat style clothing, intense stare, rarely shows emotion, driven by revenge, have weapons | Type | Rebellious, prideful, vengeful, narcissistic
Gender | Male |  | Likes | Controlling,
Hair Colour | Dark brown |  | Dislikes | Against AI systems and those who support them
Eye Colour | Green |  | Social Stance | Dominant personality, manipulative, lies to protect pride
Build | Muscular
Height | 6'0 |  | Political Stance
Weight | 90 kg |  |  | Strongly anti-AI and anti-control systems, supports rebellion against AI
Extra | Orphan, parents were killed by AI systems, former military
Psychologist
Security Officer / Police Detective
Mechanics
Doctor / Nurse
Patiant
Escaped Prisoner
Lost Child
Journalist
Character Sheet Template
Name: | Selene Lorewriter | Character Render | Personality Traits
Physical Traits |  | She carries a small notebook and pen, sometimes a satchel for documents. Find information and note it on notes to find the truth | Type | Curious, Intelligent, Brave
Gender | Female |  | Likes | Discovering hidden truths, interest interviewing people, reading, love to solve unsolved cases
Hair Colour | redish-orange hair |  | Dislikes | Lies, misinformation, corruption
Eye Colour | Blue |  | Social Stance | Friendly and approachable with most people, ask difficult questions
Build | Lean |  | Political Stance | Strong believer in truth, transparency, and freedom of information
Height | 5'6
Weight | 65kg
Extra | Formal dressing style, Journalist, young
Security Officer / Police Detective
Character Sheet Template
Name: | Samuel H. Walker | Character Render | Personality Traits
Physical Traits |  | Observation and Attention to Detail.The ability to piece together evidence and connect patterns between unrelated events | Type | Curious, Intelligent, Brave
Gender | Male |  | Likes | Discovering hidden truths, interest interviewing people, reading, love to solve unsolved cases
Hair Colour | Dark brown hair |  | Dislikes | Lies, misinformation, corruption
Eye Colour | Dark brown |  | Social Stance | Friendly and approachable with most people, ask difficult questions
Build | Muscular
Height | 6'2 |  | Political Stance | Strong believer in truth, transparency, and freedom of information
Weight | 95kg
Extra | Formal dressing style, Journalist, young